## Project
ProjectID | ProjectName | ProjectType | ClientName | ProjectManager | Location | StartDate | EndDate | ContractValue | Status
1 | ProjectA | Scaffolding | Client A | PM Smith | Edmonton | 2026-01-05 | 2026-06-30 | 270000 | Active
2 | ProjectB | Insulation | Client B | PM Brown | Calgary | 2026-01-05 | 2026-08-31 | 400000 | Active
3 | ProjectC | Shutdown | Client C | PM Wilson | Red Deer | 2026-01-05 | 2026-04-30 | 190000 | Active
4 | ProjectD | Electrical | Client D | PM Johnson | Edmonton | 2026-01-05 | 2026-06-30 | 258000 | Active
5 | ProjectE | Painting | Client E | PM Davis | Lethbridge | 2026-01-05 | 2026-06-30 | 162000 | Active
6 | ProjectF | Plumbing | Client F | PM Lee | Calgary | 2026-01-05 | 2026-06-30 | 304000 | Active
7 | ProjectG | Insulation | Client G | PM Clark | Red Deer | 2026-01-05 | 2026-06-30 | 338000 | Active
8 | ProjectH | Shutdown | Client H | PM Taylor | Edmonton | 2026-01-05 | 2026-06-30 | 366000 | Active

## cost
ProjectID | CostDate | CostCategory | BudgetCost | ActualCost | ChangeOrder | InvoiceNumber
1 | 2026-01-01 | Equipment | 50000 | 50000 | No | INV001
1 | 2026-02-01 | Labor | 60000 | 58000 | No | INV002
1 | 2026-03-01 | Material | 40000 | 36000 | Yes | INV003
1 | 2026-04-01 | Equipment | 30000 | null | null | null
1 | 2026-05-01 | Labor | 50000 | null | null | null
1 | 2026-06-01 | Material | 40000 | null | null | null | 150000 | 144000 | 6000
2 | 2026-01-01 | Labor | 60000 | 60000 | Yes | INV007
2 | 2026-02-01 | Material | 50000 | 53000 | No | INV008
2 | 2026-03-01 | Equipment | 40000 | 40000 | No | INV009
2 | 2026-04-01 | Labor | 55000 | null | null | null
2 | 2026-05-01 | Material | 45000 | null | null | null
2 | 2026-06-01 | Labor | 60000 | null | null | null
2 | 2026-07-26 | Material | 50000 | null | null | null
2 | 2026-08-26 | Equipment | 40000 | null | null | null | 150000 | 153000 | -3000
3 | 2026-01-01 | Labor | 55000 | 57000 | No | INV015
3 | 2026-02-01 | Material | 45000 | 44000 | No | INV016
3 | 2026-03-01 | Equipment | 40000 | 39000 | Yes | INV017
3 | 2026-04-01 | Labor | 50000 | null | null | null | 140000 | 140000 | 0
4 | 2026-01-01 | Labor | 50000 | 51000 | No | INV010
4 | 2026-02-01 | Material | 42000 | 43000 | No | INV011
4 | 2026-03-01 | Equipment | 35000 | 34000 | No | INV012
4 | 2026-04-01 | Labor | 52000 | null | null | null
4 | 2026-05-01 | Material | 43000 | null | null | null
4 | 2026-06-01 | Equipment | 36000 | null | null | null | 127000 | 128000 | -1000
5 | 2026-01-01 | Labor | 36000 | 39000 | No | INV013
5 | 2026-02-01 | Material | 25000 | 27000 | No | INV014
5 | 2026-03-01 | Equipment | 20000 | 21000 | Yes | INV015
5 | 2026-04-01 | Labor | 32000 | null | null | null
5 | 2026-05-01 | Material | 27000 | null | null | null
5 | 2026-06-01 | Equipment | 22000 | null | null | null | 81000 | 87000 | -6000
6 | 2026-01-01 | Labor | 55000 | 54000 | No | INV016
6 | 2026-02-01 | Material | 50000 | 51000 | No | INV017
6 | 2026-03-01 | Equipment | 45000 | 44000 | Yes | INV018
6 | 2026-04-01 | Labor | 56000 | null | null | null
6 | 2026-05-01 | Material | 51000 | null | null | null
6 | 2026-06-01 | Equipment | 47000 | null | null | null | 150000 | 149000 | 1000
7 | 2026-01-01 | Labor | 60000 | 62000 | No | INV019
7 | 2026-02-01 | Material | 55000 | 54000 | No | INV020
7 | 2026-03-01 | Equipment | 55000 | 51000 | No | INV021
7 | 2026-04-01 | Labor | 61000 | null | null | null
7 | 2026-05-01 | Material | 56000 | null | null | null
7 | 2026-06-01 | Equipment | 51000 | null | null | null | 170000 | 167000 | 3000
8 | 2026-01-01 | Labor | 65000 | 70000 | Yes | INV022
8 | 2026-02-01 | Material | 60000 | 59000 | No | INV023
8 | 2026-03-01 | Equipment | 55000 | 56000 | No | INV024
8 | 2026-04-01 | Labor | 67000 | null | null | null
8 | 2026-05-01 | Material | 62000 | null | null | null
8 | 2026-06-01 | Equipment | 57000 | null | null | null | 180000 | 185000 | -5000

## schedule
ProjectID | ReportMonth | PlannedProgress (%) | ActualProgress(%) | Milestone | DelayReason
1 | 2026-01-01 | 20 | 22 | Foundation | None
1 | 2026-02-01 | 35 | 30 | Structure | Weather
1 | 2026-03-01 | 45 | 41 | Structure | None | -4
1 | 2026-04-01 | 60 | null | Interior | null
1 | 2026-05-01 | 80 | null | Interior | null
1 | 2026-06-01 | 100 | null | Completion | null
2 | 2026-01-01 | 15 | 18 | Foundation | None
2 | 2026-02-01 | 25 | 28 | Foundation | None
2 | 2026-03-01 | 35 | 35 | Structure | Weather | 0
2 | 2026-04-01 | 50 | null | Structure | null
2 | 2026-05-01 | 65 | null | Structure | null
2 | 2026-06-01 | 80 | null | Interior | null
2 | 2026-07-26 | 90 | null | Interior | null
2 | 2026-08-26 | 100 | null | Completion | null
3 | 2026-01-01 | 20 | 25 | Foundation | None
3 | 2026-02-01 | 40 | 40 | Structure | Weather
3 | 2026-03-01 | 60 | 65 | Interior | null | 5
3 | 2026-04-01 | 100 | null | Completion | null
4 | 2026-01-01 | 10 | 10 | Foundation | None
4 | 2026-02-01 | 25 | 20 | Structure | Weather
4 | 2026-03-01 | 35 | 35 | Structure | None
4 | 2026-04-01 | 50 | 48 | Interior | Scope | -2
4 | 2026-05-01 | 70 | null | Interior | null
4 | 2026-06-01 | 90 | null | Interior | null
4 | 2026-07-26 | 100 | null | Completion | null
5 | 2026-01-01 | 20 | 20 | Foundation | None
5 | 2026-02-01 | 30 | 30 | Structure | Weather
5 | 2026-03-01 | 45 | 38 | Structure | None | -7
5 | 2026-04-01 | 65 | null | Interior | null
5 | 2026-05-01 | 80 | null | Interior | null
5 | 2026-06-01 | 100 | null | Completion | null
6 | 2026-01-01 | 15 | 18 | Foundation | None
6 | 2026-02-01 | 35 | 35 | Structure | None
6 | 2026-03-01 | 60 | 67 | Interior | None | 7
6 | 2026-04-01 | 85 | null | Interior | null
6 | 2026-05-01 | 100 | null | Completion | null
7 | 2026-01-01 | 10 | 12 | Foundation | None
7 | 2026-02-01 | 30 | 28 | Structure | Weather
7 | 2026-03-01 | 50 | 47 | Structure | None
7 | 2026-04-01 | 70 | null | Interior | null | -3
7 | 2026-05-01 | 90 | null | Interior | null
7 | 2026-06-01 | 100 | null | Completion | null
8 | 2026-01-01 | 20 | 21 | Foundation | None
8 | 2026-02-01 | 40 | 36 | Structure | Weather
8 | 2026-03-01 | 60 | 62 | Interior | None | 2
8 | 2026-04-01 | 80 | null | Interior | null
8 | 2026-05-01 | 100 | null | Completion | null

## manhours
ProjectID | WorkMonth | PlannedHours | ActualHours | Trade
1 | 2026-01-01 | 400 | 420 | Scaffold
1 | 2026-02-01 | 450 | 460 | Scaffold
1 | 2026-03-01 | 500 | 520 | Insulation
1 | 2026-04-01 | 550 | null | Electrical
1 | 2026-05-01 | 500 | null | Painting
1 | 2026-06-01 | 450 | null | Plumbing
2 | 2026-01-01 | 300 | 320 | Scaffold
2 | 2026-02-01 | 350 | 340 | Scaffold
2 | 2026-03-01 | 400 | 390 | Insulation
2 | 2026-04-01 | 450 | null | Insulation
2 | 2026-05-01 | 500 | null | Electrical
2 | 2026-06-01 | 350 | null | Plumbing
2 | 2026-07-26 | 400 | null | Plumbing
2 | 2026-08-26 | 450 | null | Painting
3 | 2026-01-01 | 300 | 310 | Scaffold
3 | 2026-02-01 | 400 | 390 | Insulation
3 | 2026-03-01 | 500 | 520 | Electrical
3 | 2026-04-01 | 450 | null | Painting
4 | 2026-01-01 | 300 | 310 | Scaffold
4 | 2026-02-01 | 350 | 360 | Scaffold
4 | 2026-03-01 | 400 | 390 | Insulation
4 | 2026-04-01 | 450 | 460 | Insulation
4 | 2026-05-01 | 400 | null | Electrical
4 | 2026-06-01 | 350 | null | Plumbing
4 | 2026-07-26 | 400 | null | Painting
5 | 2026-01-01 | 200 | 210 | Scaffold
5 | 2026-02-01 | 250 | 240 | Scaffold
5 | 2026-03-01 | 300 | 310 | Insulation
5 | 2026-04-01 | 350 | null | Electrical
5 | 2026-05-01 | 300 | null | Painting
5 | 2026-06-01 | 450 | null | Plumbing
6 | 2026-01-01 | 400 | 420 | Scaffold
6 | 2026-02-01 | 450 | 460 | Insulation
6 | 2026-03-01 | 500 | 490 | Electrical
6 | 2026-04-01 | 450 | null | Painting
6 | 2026-05-01 | 400 | null | Plumbing
7 | 2026-01-01 | 300 | 320 | Scaffold
7 | 2026-02-01 | 350 | 360 | Scaffold
7 | 2026-03-01 | 400 | 390 | Insulation
7 | 2026-04-01 | 450 | null | Electrical
7 | 2026-05-01 | 400 | null | Painting
7 | 2026-06-01 | 350 | null | Plumbing
8 | 2026-01-01 | 400 | 410 | Scaffold
8 | 2026-02-01 | 450 | 460 | Insulation
8 | 2026-03-01 | 500 | 490 | Electrical
8 | 2026-04-01 | 450 | null | Painting
8 | 2026-05-01 | 400 | null | Plumbing

## Issues
IssueID | ProjectID | IssueType | IssueDescription | CostImpact | IssueDate | ScheduleImpactDays | Status
1 | 1 | Schedule | Equipment delivery delayed due to supplier | 0 | 2026-02-10 | 7 | Open
2 | 1 | Cost | Labor overtime exceeded planned hours | 12000 | 2026-03-05 | 0 | Mitigated
3 | 2 | Procurement | Long-lead material arrived later than planned | 5000 | 2026-01-28 | 10 | Closed
4 | 2 | Scope / Change | Client requested additional inspection | 18000 | 2026-02-15 | 5 | Open
5 | 3 | Quality | Failed inspection requiring rework | 22000 | 2026-03-02 | 12 | Open
6 | 3 | Resource | Skilled labor shortage | 8000 | 2026-02-20 | 6 | Mitigated
7 | 4 | Risk Event | Weather disruption (heavy snow) | 0 | 2026-01-18 | 14 | Closed
8 | 4 | Cost | Material price increase (steel) | 30000 | 2026-02-25 | 0 | Open
9 | 5 | External | Utility relocation delayed by third party | 15000 | 2026-03-08 | 9 | Open
10 | 5 | Schedule | Milestone approval delayed | 0 | 2026-02-05 | 4 | Closed
11 | 6 | Scope / Change | Design revision issued after construction | 45000 | 2026-03-01 | 15 | Open
12 | 6 | Quality | Installation error discovered | 10000 | 2026-02-12 | 3 | Closed
13 | 7 | Procurement | Incorrect material delivered | 7000 | 2026-01-30 | 5 | Mitigated
14 | 7 | Cost | Unplanned equipment rental | 9000 | 2026-02-22 | 0 | Open
15 | 8 | Schedule | Late client decision on final layout | 0 | 2026-03-06 | 8 | Open
16 | 8 | Risk Event | Permit approval delay | 0 | 2026-01-25 | 11 | Closed