## Issues
IssueID | ProjectID | IssueType | IssueDescription | CostImpact | IssueDate | ScheduleImpactDays | Status
1 | 1 | Schedule | Equipment delivery delayed due to supplier | 0 | 2026-02-10 | 7 | Open
2 | 1 | Cost | Labor overtime exceeded planned hours | 12000 | 2026-03-05 | 0 | Mitigated
3 | 2 | Procurement | Long-lead material arrived later than planned | 5000 | 2026-01-28 | 10 | Closed
4 | 2 | Scope / Change | Client requested additional inspection | 18000 | 2026-02-15 | 5 | Open
5 | 3 | Quality | Failed inspection requiring rework | 22000 | 2026-03-02 | 12 | Open
6 | 3 | Resource | Skilled labor shortage | 8000 | 2026-02-20 | 6 | Mitigated
7 | 4 | Risk Event | Weather disruption (heavy snow) | 0 | 2026-01-18 | 14 | Closed
8 | 4 | Cost | Material price increase (steel) | 30000 | 2026-02-25 | 0 | Open
9 | 5 | External | Utility relocation delayed by third party | 15000 | 2026-03-08 | 9 | Open
10 | 5 | Schedule | Milestone approval delayed | 0 | 2026-02-05 | 4 | Closed
11 | 6 | Scope / Change | Design revision issued after construction | 45000 | 2026-03-01 | 15 | Open
12 | 6 | Quality | Installation error discovered | 10000 | 2026-02-12 | 3 | Closed
13 | 7 | Procurement | Incorrect material delivered | 7000 | 2026-01-30 | 5 | Mitigated
14 | 7 | Cost | Unplanned equipment rental | 9000 | 2026-02-22 | 0 | Open
15 | 8 | Schedule | Late client decision on final layout | 0 | 2026-03-06 | 8 | Open
16 | 8 | Risk Event | Permit approval delay | 0 | 2026-01-25 | 11 | Closed